## Slide 1: Key Risks and Mitigations
Electrification performance shortfall (temperature, throughput): - Likelihood: Medium - Impact: High - Mitigation: Pilot on one line; include fallback gas trim; thermal storage; vendor performance guarantees - Owner: VP Operations
PPA basis/price risk and counterparty credit: - Likelihood: Medium - Impact: Medium-High - Mitigation: Hub selection analysis; add basis hedge; multi-seller RFP; credit insurance - Owner: CFO / Energy Procurement
Capex overrun and schedule slip: - Likelihood: Medium - Impact: High - Mitigation: EPC wrap; 15% contingency; stage-gate FEED; weekly PMO controls - Owner: PMO
Long-lead equipment delays (transformers, switchgear): - Likelihood: High - Impact: Medium - Mitigation: Early procurement (NTP Q4); multi-source vendors; temporary rentals - Owner: Supply Chain
Policy/EAC claim changes (RECs quality, additionality): - Likelihood: Medium - Impact: Medium - Mitigation: Prioritize bundled VPPA; align with market-based reporting (GHG Protocol); annual assurance - Owner: Sustainability
Change management & operator adoption: - Likelihood: Medium - Impact: Medium - Mitigation: Formal training, SOP updates, incentive plans; kaizen cycles - Owner: Plant Manager
(Risk Matrix Chart Placeholder)